## Sheet1
DATE | CHALLENGES FACED | POINTS DISCUSSED | ACTION PLAN
03-06-2025 Agenda: Technical Planning & Role Allocation | 1. Change in Project Scope: Initial plan was based on a different project; the team had to quickly adapt to a new domain: stock options data pipelines. 2. Complex Architecture Requirements: The project mandates microservices, high availability, and observability tools, which demand clear separation of duties and robust collaboration. 3. Tool Familiarity Gap: Some team members needed to familiarize themselves with Prometheus, Grafana, and container orchestration tools like Kubernetes or Docker Swarm. 4. Rate Limitations of APIs: Need to identify an API with optimal rate limits for frequent data ingestion without hitting throttling issues. | 1. Technology Stack Selection: Considered Python (FastAPI/Flask), PostgreSQL, MongoDB, MinIO/AWS S3, Prometheus, Grafana, and Docker/Kubernetes. 2. Microservices Design & Load Balancing: No more than eight microservices; each to run in two instances with failover and load balancing using Nginx/HAProxy. 3. API Provider Research: Finnhub, Tradier, Polygon.io, Yahoo Finance and TD Ameritrade APIs were evaluated for data richness and rate limits. 4. Chaos Testing and Monitoring Needs: Discussed testing resilience by simulating failures in services, databases, and storage nodes, while ensuring continued observability. 5. Team Roles Finalization: Roles were finalized based on individual strengths and alignment with project architecture. | 1. Syed Athar Hussain (Team Lead & Scrum Master) Lead Agile sprints, manage coordination, and contribute to backend services. 2. Dimple (Data Engineering Lead) Handle API data ingestion, preprocessing, schema definition, and ETL logic. 3. Harshdeep Mahajan (Backend Developer) Build microservices for data fetch, transformation, and database interaction. 4. Girish Zarbade(Frontend Developer) Develop UI/dashboard for system monitoring and data status visualization. 5. Tanmay Shelatkar(DevOps & Testing Engineer) Implement CI/CD, orchestrate containers, set up observability and chaos tests. 6. Durga Prasad Sahoo (Backend Developer) Assist with backend service development and ensure inter-service reliability.
06-06-2025 Agenda: To finalize the foundational technical setup of the project and align on upcoming implementation tasks. | 1. The microservices-based architecture required rapid understanding and re-alignment of team responsibilities and objectives. 2. Team members had different setups, leading to inconsistencies in tools and frameworks. Establishing a common baseline environment was identified as a priority. | 1. API Evaluation by All Members: All team members agreed to individually test the recommended APIs (Finnhub, Tradier, Yahoo Finance, Polygon.io, TD Ameritrade). The team will collectively review results and finalize the most suitable API based on data coverage, rate limits, and ease of integration. 2. GitHub Repository Creation and Setup: The team discussed creating the official GitHub repository. It will include an initial README file outlining the project’s overview, microservice structure, and contribution guidelines. 3. Drafting the Data Flow Plan and Project Objectives: The team reviewed the initial concept for the system architecture and data pipeline. A working draft outlining microservice responsibilities, data flow, and storage strategy will be collaboratively developed. 4. Project Planning and Sprint Structure: The need for a structured project timeline with deliverables and milestones was emphasized. Team will create a sprint plan, including estimated deadlines for API integration, containerization, observability, and testing phases. Development Environment Configuration: Discussed the tools and environments required for microservice development and testing (e.g., FastAPI/Flask, Docker, Postman). Members agreed to individually set up local development environments including IDEs, backend frameworks, and required libraries. | 1. Test all API provider to finalize and to test authentication flow. 2. Create and Initialize GitHub repository with service folders and README. 3. Containerize and create a temporary docker file with basic requirnments using Docker. 5. Draft system architecture and pipeline diagram collaboratively. 6. Scheducle next sprint planning meeting on [08/06/2025].
2025-06-06 | 1. The team struggled to define constraints for data collection due to varying API rate limits and cost efficiency. | 1. Probal sir emphasized the importance of prioritizing system architecture and data flow planning over immediate API integration. 2. He advised the team to define project constraints clearly, especially regarding dataset size, frequency, and update intervals, before moving ahead with implementation. | 1. The team will study API documentation in detail to identify practical data constraints and finalize a well-defined data ingestion plan. 2. A detailed system architecture and execution strategy will be drafted, incorporating these constraints and aligned with project requirements.
2025-06-08 | 1. Choosing the most suitable stock options API proved challenging due to varying rate limits, data structures, and incomplete or inconsistent documentation across providers. | 1. API Finalization: After evaluating multiple options, the team finalized the most suitable API (twelve data API, Yahoo FInance) for stock options data based on rate limits, data richness, and integration ease. 2. S3 Bucket Creation: An object storage bucket (e.g., AWS S3 or compatible) was successfully created to store processed data as CSV files as per project requirements. 3. Initial CI/CD Pipeline and Docker Setup:The team decided to begin setting up the Continuous Integration/Continuous Deployment (CI/CD) pipeline. Docker will be used to containerize microservices as part of the initial infrastructure setup. | 1. Refine the data pipeline flow, clearly define project goals, constraints, and justify API and technology choices in the final draft. 2. Review and consolidate all sections including architecture, API details, system design, and observability setup to complete the final project document. 3. Ensure all required documents (MoM, architecture diagram, data plan, objective, etc.) are submitted on time to the project coordinator or designated portal.
2025-06-09 |  | 1. Submitted all the required documents. 2. Discussed further task for the upcoming team workshop.
2025-06-12 | 1. Uncertainty about which database services best fit different types of data (e.g., historical vs. day-wise). 2. Performance concerns with PostgreSQL for large datasets — indexing strategies need optimization. 3. Need for clarity on Kafka integration across microservices. 4. Complexity in deciding where and how to store long-term historical data — S3 vs. static PostgreSQL tables. | 1. Evaluated various database options based on use cases: a. PostgreSQL for relational/day-wise data b. InfluxDB for time-series data c. S3 for storing large CSV files and historical data 2. Team members explored different service providers: a. Azure (Postgres hosting) b. AWS (S3, RDS) c. Google Cloud d. InfluxDB Cloud 3. Kafka’s role in microservice communication was discussed, along with strategies for integration. 4. Defined key fields and discussed schema/data model design for the database. 5. Importance of indexing in PostgreSQL to improve query performance was emphasized. 6. UI/UX planning began with reference to yFinance, to be implemented using React. 7. Discussion on using Prometheus and Grafana for monitoring and data visualization. 8. Talked through Dockerfile structure for microservices and deployment using Kubernetes. 9. Clarified roles of PostgreSQL vs. InfluxDB for frontend visualizations and real-time data insights. 10. Debated between using S3 or a static PostgreSQL table for storing historical data. 11. Agreed that databases will be initialized and managed via the writer service. | 1. Finalize the data model including: a. Columns for each table b. Indexing strategy for PostgreSQL c. Schema for time-series storage in InfluxDB 2. Team members to prototype database setup on: a. Azure PostgreSQL instance b. InfluxDB local/cloud setup c. S3 bucket configuration for historical data 3. Begin integrating Kafka into the architecture for event-driven communication between services. 4. Start setting up Prometheus and Grafana monitoring stack. 5. Define how Dockerfiles will be structured per microservice and set up Kubernetes manifests. 6. UI team to start wireframing frontend components using React based on yFinance reference. 7. Finalize decision on storing historical data — static tables vs. S3 — based on access needs and performance. 8. Implement the initial version of the writer service to create and update the necessary databases.
2025-06-13 | 1. Team members encountered roadblocks while implementing parts of their tasks and required mutual support. 2. Lack of clarity on the complete data pipeline structure initially caused minor confusion in scheduling and dependencies. | 1. Identified and finalized the scheduling jobs required across services. 2. Discussed the core methods/functions needed for: a. Collector: Data fetching strategy b. Processor: Data cleaning/transformation logic c. Writers: Database and file output handling 3. Discussed and initiated setup for the Dockerfile for containerization. 4. Designed a rough flow diagram outlining interactions between five key services: a. Scheduler b. Collector c. Processor d. DB Writer e. File Writer 5. Assigned specific responsibilities to each team member and updated the Jira board accordingly. 6. Discussed how options data should be presented on the dashboard for clear visibility. 7. Finalized the data flow plan for implementation. | 1. Begin development of scheduling mechanisms and link them to respective services. 2. Each team member to start implementing their assigned component (Collector, Processor, Writers). 3. Set up and test Docker containers for each microservice. 4. Use the drafted flow diagram as a blueprint for coding and system integration. 5. Continue daily stand-ups or syncs to ensure blockers are addressed quickly. 6. Start implementing the finalized data plan and track progress through Jira. 7. Plan for next meeting to demo partial integration and review dashboard progress.
2025-06-16 | 1. Limited time for syncing frontend with live backend data (dashboard still uses dummy data). 2. Minor integration delays between the data processor and database writer, now resolved. 3. Difficulty in aligning frontend visuals with backend data structure. | 1. Reviewed progress on both backend and frontend development. 2. Confirmed that four backend services have been successfully completed: a. Airflow Scheduler b. Data Collector c. Data Processor d. Database Writer 3. Agreed that all four services should be included in the interim presentation to showcase technical milestones. 4. Evaluated the frontend dashboard, currently working with dummy data, and confirmed it will also be shown during the interim demo. 5. Discussed and finalized the key points/content to be included in the interim presentation PowerPoint (PPT). 6. Initiated the process of creating the PPT, assigning responsibilities for different sections. | 1. Finalize and polish the interim PPT, including diagrams and descriptions of all backend services. 2. Prepare demo-ready views of the frontend dashboard, even if backed by dummy data. 3. Assign team members to present specific backend modules during the presentation. 4. Plan next sprint for live data integration with the frontend dashboard. 5. Conduct a mock presentation before the final interim demo.
2025-02-20 | 1. Initial PPT lacked visual consistency and missed a few technical highlights. 2. Some members faced difficulty syncing their verbal explanations with the content shown in the slides. 3. Limited time available to record, edit, and submit the demo before the deadline. | 1. Reviewed the first draft of the interim presentation PPT. 2. Finalized what additional content needs to be added to the slides for better clarity and completeness. 3. Discussed and agreed upon theme changes (visual style, color palette, font consistency) to enhance the presentation’s aesthetics. 4. Planned to record a demo video of the interim presentation for submission. 5. Allocated specific sections of the presentation to each team member for delivery during the recording. 6. Team agreed on maintaining flow and continuity during the demo by rehearsing transitions between speakers. | 1. Update the PPT with final content and apply the agreed theme and design changes. 2. Schedule and conduct a rehearsal session to align speaking parts and transitions. 3. Record the interim presentation demo video, ensuring clarity, timing, and technical accuracy. 4. Complete video editing (if needed) and submit the demo before the assigned deadline. 5. Ensure all team members are familiar with the content of their assigned sections and ready to present confidently.
2025-06-23 | 1. Minor inconsistencies in the initial version of the combined demo. 2. Time pressure to complete script finalization and video editing before submission. 3. Coordination across team members to ensure a unified tone in the script and presentation. | 1. Reviewed the final draft of the interim presentation PPT, scheduled to be presented on 24/06/2024. 2. Presented the recorded demo video created by all team members. 3. Discussed and implemented necessary edits to merge and smoothen the full demo recording, ensuring consistency in flow and transitions. 4. Worked collectively on finalizing the presentation script, refining each member’s speaking part for clarity and time management. 5. Ensured alignment between script, slides, and demo for a cohesive presentation delivery. | 1. Finalize and submitted the merged demo video after incorporating edits. 2. Conduct a quick rehearsal before the live presentation to ensure confidence and clarity. 3. All team members to review their script parts one last time and be prepared for potential Q&A during the interim review session.
2025-06-27 | 1. Frontend database integration through Angular was causing technical conflicts and instability. 2. Lack of abstraction between backend logic and frontend components led to coupling and error propagation. 3. Some backend services still pending implementation or testing, affecting full-stack flow. | 1. Reviewed the status of remaining backend services that are yet to be completed. 2. Discussed data integration efforts for the frontend, including real-time and historical data display. 3. Identified integration issues between Angular and direct database access, which were causing conflicts. 4. Agreed that the backend team will create API services to resolve the frontend-backend integration challenge and fetch data. 5. Planned the next sprint, with tasks assigned based on pending modules and integration goals. | 1. Backend team to design and deploy API services to expose necessary data for the frontend securely and efficiently. 2. Frontend team to integrate APIs via Angular services, replacing direct database calls. 3. Define and assign clear tasks for the next sprint, focusing on: a. Completing the remaining backend services, b. Finalizing frontend data visualizations, c. Ensuring stable integration across modules. 4. Schedule a follow-up review session to validate progress and prepare for the next project milestone.
2025-07-07 | 1. Need to manage API key limits and scheduling efficiently to avoid rate limiting while scaling. 2. UI adjustments and data mapping on the dashboard required refinement after API integration. 3. Monitoring setup is partial; Grafana and Prometheus integration is only complete for the data collector, not for other services. | Reviewed overall progress across frontend, backend, and supporting services. 1. Backend Update: a. Implemented multithreading to efficiently handle 120 stock symbols using 5 Twelve Data API keys, with each key handling 24 symbols every 3 minutes. b. Completed the File Writer service. c. Data Collector service is successfully pushing B13 to Prometheus and Grafana for monitoring. 2. Frontend Update: a. Successfully integrated APIs to fetch real-time data from backend. b. Discussed UI enhancements and remaining adjustments needed on the dashboard layout and presentation. 3. Identified remaining backend components such as: a. B13Load Balancer service b. Additional Monitoring and Observability features not yet implemented | 1. Backend team to: a. Complete Load Balancer implementation. b. Extend Prometheus and Grafana integration to remaining services for full-stack observability. 2. Frontend team to: a. Finalize UI changes based on the feedback discussed. b. Ensure proper rendering of dynamic data on the dashboard with error handling. 3. Perform testing for multithreaded data collection, ensuring stability under production load. 4. Plan next meeting to review full system integration before final delivery milestones
2025-07-15 | 1. Azure deployment configuration needed additional setup time and expertise. 2. Defining and structuring performance metrics for large datasets (month/year wise) posed complexity. 3. Failover strategy research revealed gaps in current system resilience planning. 4. Integrating new UI features while maintaining frontend stability required coordination with API state. | 1. Deployment setup on Azure was planned and discussed. 2. Setup of Load Balanced Service for backend stability. 3. Identified the need to analyze performance metrics by loading data month-wise and year-wise. 4. Research began on possible failover recovery strategies for high availability. 5. In the frontend, a search bar was proposed for the dashboard to improve UX. 6. Based on feedback from the interim presentation, the team decided to start working on: a) The final presentation b) Project documentation | 1. Complete Azure deployment setup by end of this sprint and ensure accessibility for all services. 2. Finalize and implement the load-balanced backend architecture. 3. Continue with detailed performance benchmarking, specifically focusing on time-based data loads. 4. Deep dive into failover mechanisms. 5. Add search bar functionality to dashboard using Angular and connect it to existing API. 6. Assign sections and begin content creation for final presentation and project report.